## Slide 1
Pass In Review
Air Force ROTC Detachment 842
The University of Texas at San Antonio
C/Vallor and C/Al Luhaibat
04 Dec. 2024

## Slide 2
Overview
Air Force ROTC Detachment 842 • We Build Exceptional Officers • The University of Texas at San Antonio
Placemat
POC Roles
POC Timeline
Supplementary Info
Diagram
Questions

## Slide 3
Timeline:
13Oct 2024
Disseminate Information with A3
05Nov2024
Initial practice with Command Staff
12/14thNov2024
Initial practice with ALL POC
19, 21Nov2024 and 3Dec2024
PT Practices
21NOV2024
1700: Official Wing Practice
05DEC2024
1600: LLAB team + Add ComSup personnel arrive
1615: Gates Open
1645: Pass In Review Begins
1735: Pass In Review Concludes
Mission:
UTSA Det 842 will be conducting our inaugural Pass and Review. This event is the culmination of the semester, and will include the changing of command and the review of the Wing by the Commander.
Concept of the Operation:
  Flights will form up at the Park West field by 1645 on 05 December 2024. Accountability will be taken. We will then conduct the changing of command, showcase warrior and honor flight and finally conduct pass and review.
CONOPS:
Pass In Review
Coordinating Instructions
UNIFORM: Blues/Alternates
VEHICLES:GOV to transfer equipment/Personal Vehicles
EQUIPMENT: Speakers, microphones, cones
COMMUNICATION: Slack
FUNDING: Detachment
Units Tasked:
INTERNAL:
GMC: All Flights
POC: All Flights
EXTERNAL:
UTSA Staff
Tasks to Staff:
Force Protection: Safety
Logistics - Transportation, uniforms
Operations - Review and Conduct D&C
Public Affairs - Provide media coverage (photos/videos), update social media sites
Risk Assessment
Hazard | Initial Risk Level | Mitigated Risk Level
Tripping | Med | Low
Cars/Traffic | Low | Low
Heat Stress | Med | Low
DATE/TIME IDENTIFIED | VENUE CONFIRMED | TRANSPORTATION CONFIRMED | GUESTS CONFIRMED
RECON CONDUCTED | INFORMATION SENT | REHEARSAL CONDUCTED | AAR CONDUCTED

## Slide 4
POC Roles
Air Force ROTC Detachment 842 • We Build Exceptional Officers • The University of Texas at San Antonio
A5:
  Assist in setting up seats on the field for cadre and distinguished visitors
  Control guest traffic -> direct to bleachers
    get aid from Addition ComSup Personnel if needed
    assist those with special accommodations (wheelchair/walker)
  Once the event has started: Maintain Perimeter Security under Force Protection
Force Protection:
  Lead and Maintain Perimeter Security during the event

## Slide 5
Timeline
Air Force ROTC Detachment 842 • We Build Exceptional Officers • The University of Texas at San Antonio
1500-1600: Arrive and Set Up at Parkwest
1615: Cadets Arrive
  A3 Accountability Completed by: 1630
1630: Gates Open to Guests
1640: Flights Should be in Position on Field
1645: Start of PIR
1735: Conclusion of PIR
1745-1800: Take down/Potluck

## Slide 6
Supp. Info
Air Force ROTC Detachment 842 • We Build Exceptional Officers • The University of Texas at San Antonio
UOD: Blues/Service Dress
Field Seats:
  3 from UTSA
  1 from Region
  10 Cadre
  5 Command Staff
Those not in A3/A5/Force Protection should report to POC flight for the event

## Slide 7
Soccer Field Diagram
Air Force ROTC Detachment 842 • We Build Exceptional Officers • The University of Texas at San Antonio
Audience
Sqd 1
Sqd 2
Field Seats
Field Seats
= Force Protection Posts

## Slide 8: Questions?